## DG301_W7P2U_INT3.5.0RC1-150602_1223
Test Plan

Device: DG301A / Firmware: DG301-W7P2U_INT3.5.0RC1-150602_1123
ID	Mode	Menu	Sub-menu	Function	test case	Expected Result	Tested	Status					Comment
					Firefox				Chrome				IE		Opera
					W7	W8	Linux	Mac	W7	W8	Linux	Mac	W7	W8	Mac
1	Basic/Expert	Login		Authentication	Login with correct user and password. Access permitted	Login	1	1		1		1		1		1	-1	-1
2	Basic/Expert	Login		Authentication	Login with incorrect user and/or password. Access denied	Denied	1	1		1		1		1		1	-1	-1
3	Basic/Expert	Logout		Logout	logout	logout	1	1		1		1		1		1	-1	-1
4	Basic/Expert	Language		Language	Switch from English to Swedish	Content displayed in Swedish	1					-1	-1
5	Basic/Expert	Language		Language	Switch from Swedish to English	Content displayed in English	1	1		1		1		1		1	-1	-1
6	Basic/Expert	Top Menu		Select list	Color of selected option	Selected option must be in Vodaphone colors	1	1		1		1		1		1	-1	-1	Color of selected option is blue
7	Basic/Expert	Menu		Check Menu	List of menu	Overview / Phone / Internet / Wifi / Settings / Status	1	1		1		1		1		1	-1	-1
8	Basic/Expert	Overview		Device	Device image	Show the image of the device	1	1		1		1		1		1
9	Basic/Expert	Overview		Uplink Type	Adsl	Adsl label and rates are shown	1	0		0		0		0		0	-1	-1	If the window resolution is minimized the uplink type is hidden
10	Basic/Expert	Overview		Uplink Type	Vdsl	Vdsl label and rates are shown	1					-1	-1
11	Basic/Expert	Overview		Uplink Type	LTE	LTE label and squality image are shown	1	0		0		0		0		0	-1	-1	Firmware issue. LTE connection is not detected
12	Basic/Expert	Overview	Wifi	Schedule	Disable and Enable Schedule.	Status is updated on Schedule page of Wifi menu	1	0		0		0		0		0	-1	-1	Schedule Button (ON/OFF) does not work
13	Basic/Expert	Overview	Wifi	WPS	Disable and Enable WPS.	Status is updated on WPS page of Wifi menu	1	1		1		1		1		1	-1	-1
14	Basic/Expert	Overview	Ethernet	Ethernet	IP list of connected devices	IP are get from ubus call router clients	1	0		0		0		0		0	-1	-1	The icon is always of a PC. Even if the connected device is Smart phone, …	There is currently no way to detect connected device.
15	Basic/Expert	Overview	Phone	Phone	Disable and Enable Schedule.	Status is updated on Schedule page of Wifi menu	1	1		1		1		1		1	-1	-1
16	Basic/Expert	Phone	Call Log					-1	-1
17	Expert	Phone	Number blocking					-1	-1
18	Expert	Phone	Ringing Schedule					-1	-1
19	Expert	Phone	Phone Numbers					-1	-1
20	Expert	Phone	Phone lines					-1	-1
21	Expert	Phone	Speed dialing					-1	-1
22	Basic/Expert	Internet	Firewall	Enable/Disable	Enable/Disable firewall		1	1		1		1		1		1	-1	-1	Since firewall will be enabled when Exposed host function is enable. It is better that an alert message is shown when we try to disable firewall
23	Expert	Internet	Port mapping	Add	Add new empty row with no selected device and ports start and stop are 0 and.	Add denied	1	1		1		1		1		1	-1	-1	I think that adding empty row should be denied. Also, deny adding empty device or port equal to 0
24	Expert	Internet	Port mapping	Add	Add new port with TCP protocol and single port	Add done	1	1		1		1		1		1	-1	-1
25	Expert	Internet	Port mapping	Add	Add new port with UDP protocol with single port	Add done	1	1		1		1		1		1	-1	-1
26	Expert	Internet	Port mapping	Add	Add new port with TCP protocol with port range	Add done	1	1		1		1		1		1	-1	-1
27	Expert	Internet	Port mapping	Add	Add new port with UDP protocol with port range	Add done	1	1		1		1		1		1	-1	-1
28	Expert	Internet	Port mapping	Edit	Select row and modify selected device	Device of selected row is modified	1	1		1		1		1		1	-1	-1
29	Expert	Internet	Port mapping	Edit	Select row modify the local IP	IP of selected IP is modified	1	1		1	1	1	1	1	1	1	-1	-1	Is the Local IP depend on available IP in list of slected device?	What is meant by this?
30	Expert	Internet	Port mapping	Edit	Select row and modify protocol	Protocol is updated	1	1		1		1		1		1	-1	-1
31	Expert	Internet	Port mapping	Edit	Select row with single port. Edit port	Port updated	1	1		1		1		1		1	-1	-1
32	Expert	Internet	Port mapping	Edit	Select row with single port. Select port range and edit start and stop ports	Port moved to port range	1	1		1		1		1		1	-1	-1
33	Expert	Internet	Port mapping	Edit	Select row with port range. Edit port range	Ports are updated	1	1		1		1		1		1	-1	-1
34	Expert	Internet	Port mapping	Delete	Delete row	Row deleted	1	1		1		1		1		1	-1	-1
35	Expert	Internet	Port mapping	Cancel	Click on add button edit something and click on cancel	Add canceled	1	1		1		1		1		1
36	Expert	Internet	Exposed host	Enable/Disable	Enable exposed host function	Enable done and firewall is enabled	1	1		1		1		1		1	-1	-1
37	Expert	Internet	Exposed host	Local IP	Add valid IP address	Edit done	1	1		1		1		1		1	-1	-1
38	Expert	Internet	Exposed host	Local IP	Add invalid IP address	Add fails	1	0		0		0		0		0	-1	-1	Invalid IP is permitted
39	Expert	Internet	DNS&DDNS	DNS configuration	Select Automatic option	DNS servers items are hidden	1	1		1		1		1		1	-1	-1
40	Expert	Internet	DNS&DDNS	DNS configuration	Select Manual option	DNS servers items are displayed	1	1		1		1		1		1
41	Expert	Internet	DNS&DDNS	DNS servers	Add valid IP	Done	1	1		1		1		1		1
42	Expert	Internet	DNS&DDNS	DNS servers	Add invalid IP address	Denied	1	0		0		0		0		0			Invalid IP is permitted
43	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Enable Dynamic DNS	Related Items are shown	1	1		1		1		1		1
44	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Select provider	Done	1	1		1		1		1		1
45	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Check the checkbox Enter DNS provider	Provider select list become text area.	1	1		1		1		1		1
46	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Check the checkbox Enter DNS provider and Add provider	New provider is added.	1	0		0		0		0		0			If the page is refreshed, the added provider is not shown
47	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Add domain name	Done	1	1		1		1		1		1
48	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Add username	Done	1	1		1		1		1		1
49	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Add password	Done	1	1		1		1		1		1
50	Basic/Expert	Wifi	General	Wifi network	Enable wifi network	Wifi network is enabled and Setup section is shown	1	1		1		1		1		1	-1	-1
51	Basic/Expert	Wifi	General	Wifi network	Disable wifi network	Wifi network is disabled and Setup section is hidden	1	1		1		1		1		1
52	Basic/Expert	Wifi	General	Enable WiFi On/Off button on EasyBox	Enable Dynamic DNS	Done	1	1		1		1		1		1
53	Basic/Expert	Wifi	General	Setup	Disable wifi network	related Items are hidden. And network is hidden	1	1		1		1		1		1
54	Basic/Expert	Wifi	General	Setup	Enable wifi network	related Items are hidden. And network is hidden	1	1		1		1		1		1
55	Basic/Expert	Wifi	General	Setup	Modify SSID	new ssid is shown	1	1		1		1		1		1
56	Basic/Expert	Wifi	General	Setup	Make protection mode off	Related Item are hiden .Connection made without password.	1	1		1		1		1		1
57	Basic/Expert	Wifi	General	Setup	Make protection mode WEP/WPA/WPA2/WPA+WPA2	Password text area is shown. Connection made with configured password	1	1		1		1		1		1
58	Basic/Expert	Wifi	General	Setup	Check checkbox Display caracter	password characters are shown	1	1		1		1		1		1
59	Basic/Expert	Wifi	General	Setup	Uncheck checkbox Display caracter	password characters replaced by “*”	1	1		1		1		1		1
60	Basic/Expert	Wifi	Schedule	schedule function	Enable Schedule function	Setup Scheduling is shown. / schedule is shown enabled in overview page. / An inform message is displayed in general page of wifi menu.	1	1		1		1		1		1	-1	-1
61	Basic/Expert	Wifi	Schedule	schedule function	Disable Schedule function	Setup Scheduling is hidden. / Schedule is shown disabled in overview page	1	1		1		1		1		1
62	Basic/Expert	Wifi	Schedule	Setup Scheduling	Add new empty Wifi schedule	Denied	1	1		1		1		1		1
63	Basic/Expert	Wifi	Schedule	Setup Scheduling	Add new Wifi schedule: / - Time Frame: indivual days / - No day checked / - No time range	Denied	1	1		1		1		1		1
64	Basic/Expert	Wifi	Schedule	Setup Scheduling	Add new Wifi schedule: / - Invalid Time range	Denied	1	1		1		1		1		1
65	Basic/Expert	Wifi	Schedule	Setup Scheduling	Add new Wifi schedule: / - Time Frame: indivual days / - Select one day / - Edit time range	Done	1	0		0		0		0		0			If we try to add a second wifi schedule the first one is displayed by default.
66	Basic/Expert	Wifi	Schedule	Setup Scheduling	Modify Wifi schedule Time frame	Time Frame modifed. And Checkbox are modified depending on the selected time frame	1	0		0		0		0		0			The displayed dialogue popup title is “Add a new Wifi Schedule”. But we are going to edit not to add new one. / If the selected schedule Time Frame is “Individual Days” It is not displayed in the dialogue popup.
67	Basic/Expert	Wifi	Schedule	Setup Scheduling	Delete row	Schedule deleted	1	1		1		1		1		1
68	Basic/Expert	Wifi	WPS	WPS	Disable WPS Function	Related Items are hidden. WPS status is updated in overview page	1	1		1		1		1		0	-1	-1	WPS status is not updated on overview page
69	Basic/Expert	Wifi	WPS	WPS	Enable WPS function	Related Items are shown. WPS status is updated on overview page	1	1		1		1		1		0			WPS status is not updated on overview page
70	Basic/Expert	Wifi	WPS	WPS	Enable and Disable available Wifi networks		1	1		1		1		1		1
71	Basic/Expert	Wifi	WPS	WPS-PBC:Push Button On device	Enable WPS button on router And Enable push on/off button of the router for long time click on pair.	After 2 minutes, WPS led blinking and popup is displayed. Device is connected with WPS	1	0		0		0		0		0			Connection to the available wifi network with WPS fails
72	Basic/Expert	Wifi	WPS	WPS-PBC:Push Button On device	Disable WPS Using Generated PIN	related Items are hidden.	1	1		1		1		1		1
73	Basic/Expert	Wifi	WPS	WPS-PBC:Push Button On device	Enable WPS Using Generated PIN Edit pin code in generated PIN	Pin text input is not editable	1	0		0		0		0		0			generated PIN is editable, but is we remove content of text input and try ti generated we can't generate PIN code
74	Basic/Expert	Wifi	WPS	WPS-PIN: Another Device provides PIN	Generate PIN	Pin generated with 8 digit	1	1		1		1		1		1
75	Expert	Wifi	Mac filter					-1	-1
76	Expert	Wifi	Settings					-1	-1
77	Basic/Expert	Settings	EasyBox password					-1	-1
78	Basic/Expert	Settings	Firmware Upgrade					-1	-1
79	Basic/Expert	Settings	Energy Settings					-1	-1
80	Basic/Expert	Settings	Configuration					-1	-1
81	Expert	Settings	network					-1	-1
82	Basic/Expert	Status	Status:System					-1	-1
83	Basic/Expert	Status	Status:DSL					-1	-1
84	Basic/Expert	Status	Status:Voice					-1	-1
85	Basic/Expert	Status	Status:Vodafone TV					-1	-1
86	Basic/Expert	Status	Diagnostics					-1	-1
87	Expert	Status	Events					-1	-1
88	Basic/Expert	Status	Restart					-1	-1
89	Basic/Expert	Status	About					-1	-1
90	Expert	Status	NAT					-1	-1
Total					68	55	0	55		55	1	55	1	53	-56	-56

## CG300-WU21U_INT3.5.0RC1-150602_1121
Test Plan

Device: DG300 / Firmware: CG300-WU21U_INT3.5.0RC1-150602_1121
ID	Mode	Menu	Sub-menu	Function	test case	Expected Result		Status					Comment
					Firefox				Chrome				IE		Opera
					W7	W8	Linux	Mac	W7	W8	Linux	Mac	W7	W8	Mac
1	Basic/Expert	Login		Authentication	Login with correct user and password. Access permitted	Login
2	Basic/Expert	Login		Authentication	Login with incorrect user and/or password. Access denied	Denied
3	Basic/Expert	Logout		Logout	logout	logout
4	Basic/Expert	Language		Language	Switch from English to Swedish	Content displayed in Swedish
5	Basic/Expert	Language		Language	Switch from Swedish to English	Content displayed in English
6	Basic/Expert	Top Menu		Select list	Color of selected option	Selected option must be in Vodaphone colors
7	Basic/Expert	Menu		Check Menu	List of menu	Overview / Phone / Internet / Wifi / Settings / Status
8	Basic/Expert	Overview		Device	Device image	Show the image of the device
8	Basic/Expert	Overview		Uplink Type	Adsl	Adsl label and rates are shown
9	Basic/Expert	Overview		Uplink Type	Vdsl	Vdsl label and rates are shown
10	Basic/Expert	Overview		Uplink Type	LTE	LTE label and squality image are shown
11	Basic/Expert	Overview	Wifi	Schedule	Disable and Enable Schedule.	Status is updated on Schedule page of Wifi menu
12	Basic/Expert	Overview	Wifi	WPS	Disable and Enable WPS.	Status is updated on WPS page of Wifi menu
13	Basic/Expert	Overview	Ethernet	Ethernet	IP list of connected devices	IP are get from ubus call router clients
14	Basic/Expert	Overview	Phone	Phone	Disable and Enable Schedule.	Status is updated on Schedule page of Wifi menu
15	Basic/Expert	Phone	Call Log
16	Expert	Phone	Number blocking
17	Expert	Phone	Ringing Schedule
18	Expert	Phone	Phone Numbers
19	Expert	Phone	Phone lines
20	Expert	Phone	Speed dialing
21	Basic/Expert	Internet	Firewall	Enable/Disable	Enable/Disable firewall
22	Expert	Internet	Port mapping	Add	Add new empty row with no selected device and ports start and stop are 0 and.	Add denied
23	Expert	Internet	Port mapping	Add	Add new port with TCP protocol and single port	Add done
24	Expert	Internet	Port mapping	Add	Add new port with UDP protocol with single port	Add done
25	Expert	Internet	Port mapping	Add	Add new port with TCP protocol with port range	Add done
26	Expert	Internet	Port mapping	Add	Add new port with UDP protocol with port range	Add done
27	Expert	Internet	Port mapping	Edit	Select row and modify selected device	Device of selected row is modified
28	Expert	Internet	Port mapping	Edit	Select row modify the local IP	IP of selected IP is modified
29	Expert	Internet	Port mapping	Edit	Select row and modify protocol	Protocol is updated
30	Expert	Internet	Port mapping	Edit	Select row with single port. Edit port	Port updated
31	Expert	Internet	Port mapping	Edit	Select row with single port. Select port range and edit start and stop ports	Port moved to port range
32	Expert	Internet	Port mapping	Edit	Select row with port range. Edit port range	Ports are updated
33	Expert	Internet	Port mapping	Delete	Delete row	Row deleted
34	Expert	Internet	Port mapping	Cancel	Click on add button edit something and click on cancel	Add canceled
35	Expert	Internet	Exposed host	Enable/Disable	Enable exposed host function	Enable done and firewall is enabled
36	Expert	Internet	Exposed host	Local IP	Add valid IP address	Edit done
37	Expert	Internet	Exposed host	Local IP	Add invalid IP address	Add fails
38	Expert	Internet	DNS&DDNS	DNS configuration	Select Automatic option	DNS servers items are hidden
39	Expert	Internet	DNS&DDNS	DNS configuration	Select Manual option	DNS servers items are displayed
40	Expert	Internet	DNS&DDNS	DNS servers	Add valid IP	Done
41	Expert	Internet	DNS&DDNS	DNS servers	Add invalid IP address	Denied
42	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Enable Dynamic DNS	Related Items are shown
43	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Select provider	Done
44	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Check the checkbox Enter DNS provider	Provider select list become text area.
45	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Check the checkbox Enter DNS provider and Add provider	New provider is added.
46	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Add domain name	Done
47	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Add username	Done
48	Expert	Internet	DNS&DDNS	DDNS (Dynamic DNS)	Add password	Done
49	Basic/Expert	Wifi	General	Wifi network	Enable wifi network	Wifi network is enabled and Setup section is shown
50	Basic/Expert	Wifi	General	Wifi network	Disable wifi network	Wifi network is disabled and Setup section is hidden
51	Basic/Expert	Wifi	General	Enable WiFi On/Off button on EasyBox	Enable Dynamic DNS
52	Basic/Expert	Wifi	General	Setup	Disable wifi network	related Items are hidden. And network is hidden
53	Basic/Expert	Wifi	General	Setup	Enable wifi network	related Items are hidden. And network is hidden
54	Basic/Expert	Wifi	General	Setup	Modify SSID	new ssid is shown
55	Basic/Expert	Wifi	General	Setup	Make protection mode off	Related Item are hiden .Connection made without password.
56	Basic/Expert	Wifi	General	Setup	Make protection mode WEP/WPA/WPA2/WPA+WPA2	Password text area is shown. Connection made with configured password
57	Basic/Expert	Wifi	General	Setup	Check checkbox Display caracter	password characters are shown
58	Basic/Expert	Wifi	General	Setup	Uncheck checkbox Display caracter	password characters replaced by “*”
59	Basic/Expert	Wifi	Schedule	schedule function	Enable Schedule function	Setup Scheduling is shown. / schedule is shown enabled in overview page. / An inform message is displayed in general page of wifi menu.
60	Basic/Expert	Wifi	Schedule	schedule function	Disable Schedule function	Setup Scheduling is hidden. / Schedule is shown disabled in overview page
61	Basic/Expert	Wifi	Schedule	Setup Scheduling	Add new empty Wifi schedule	Denied
62	Basic/Expert	Wifi	Schedule	Setup Scheduling	Add new Wifi schedule: / - Time Frame: indivual days / - No day checked / - No time range	Denied
63	Basic/Expert	Wifi	Schedule	Setup Scheduling	Add new Wifi schedule: / - Invalid Time range	Denied
64	Basic/Expert	Wifi	Schedule	Setup Scheduling	Add new Wifi schedule: / - Time Frame: indivual days / - Select one day / - Edit time range	Done
65	Basic/Expert	Wifi	Schedule	Setup Scheduling	Modify Wifi schedule Time frame	Time Frame modifed. And Checkbox are modified depending on the selected time frame
66	Basic/Expert	Wifi	Schedule	Setup Scheduling	Delete row	Schedule deleted
67	Basic/Expert	Wifi	WPS	WPS	Disable WPS Function	Related Items are hidden. WPS status is updated in overview page	1			1		1		1		0			WPS status is not updated on overview page
68	Basic/Expert	Wifi	WPS	WPS	Enable WPS function	Related Items are shown. WPS status is updated on overview page	1			1		1		1		0			WPS status is not updated on overview page
69	Basic/Expert	Wifi	WPS	WPS	Enable and Disable available Wifi networks		1			1		1		1		1
70	Basic/Expert	Wifi	WPS	WPS-PBC:Push Button On device	Enable WPS button on router And push on/off button of the router for long time.	WPS led is blinking
71	Basic/Expert	Wifi	WPS	WPS
72	Basic/Expert	Wifi	WPS	WPS
73	Basic/Expert	Wifi	WPS	WPS Function
74	Basic/Expert	Wifi	WPS	WPS Function
75	Basic/Expert	Wifi	WPS	WPS Function
76	Basic/Expert	Wifi	WPS	WPS Function
77	Basic/Expert	Wifi	WPS	WPS Function
78
79
80
81
82
83
84
85
86
87	Expert	Wifi	Mac filter
88	Expert	Wifi	Settings
89	Basic/Expert	Settings	EasyBox password
90	Basic/Expert	Settings	Firmware Upgrade
91	Basic/Expert	Settings	Energy Settings
92	Basic/Expert	Settings	Configuration
93	Expert	Settings	network
94	Basic/Expert	Status	Status:System
95	Basic/Expert	Status	Status:DSL
96	Basic/Expert	Status	Status:Voice
97	Basic/Expert	Status	Status:Vodafone TV
98	Basic/Expert	Status	Diagnostics
99	Expert	Status	Events
100	Basic/Expert	Status	Restart
101	Basic/Expert	Status	About
102	Expert	Status	NAT
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
					3	0	0	3		3	0	3	0	1	0	0